## Slide 1: Project Manager Case Study Presentation
Digitization and Automation of Procurement Process
Candidate: [Your Name] | Role: Project Manager | Date: [Insert Date]

## Slide 2: Executive Summary
• Client project to digitize and automate procurement processes using Microsoft Power Platform.
• Project scope: Replace manual forms and approval workflows with automated solutions.
• Estimated duration: 16 weeks + 2 weeks hypercare.
• Budget: $75,000 cost vs. $150,000 revenue.
• High visibility project, strategic for future engagements.

## Slide 3: Kickoff Meeting Strategy
• Objectives: Build rapport, align expectations, clarify roles.
• Agenda: Introductions, scope reaffirmation, milestones, collaboration model.
• Tools: Microsoft Teams, Miro, SharePoint.
• Outcome: Strong alignment and clear communication plan.

## Slide 4: Payment & Invoicing Milestones
• Milestone 1 – Project Initiation & BRD Signoff – 15%
• Milestone 2 – Design Completion – 20%
• Milestone 3 – Development Phase 1 – 25%
• Milestone 4 – UAT Signoff – 25%
• Milestone 5 – Go-Live & Hypercare End – 15%
• Note: Invoices payable 60 days post-issuance.

## Slide 5: Customer Confidence Strategy
• Deliver quick wins (e.g., first form automation).
• Weekly demos and transparent reporting.
• Assign SPOC on both sides.
• Proactive risk and dependency management.

## Slide 6: Project Health & Profitability Reporting
• Power BI dashboard mockup.
• KPIs: % completion, budget usage, resource efficiency.
• Traffic light indicators for health status.
• Invoice and profit margin tracking.

## Slide 7: Project Challenges - Root Cause Analysis
• New requirements delaying BRD signoff.
• Complex integrations causing technical delays.
• Budget overrun due to extended hours.
• Low performance quality in early testing.
• Communication breakdown across teams.

## Slide 8: Plan to Realign Schedule
• Revised timeline with priority-based phasing.
• Parallel workstreams for new and existing scope.
• Fast-track priority forms for early UAT.
• Daily standups and weekly steering meetings.

## Slide 9: Managing Budget Overruns
• Introduce formal change requests for scope increase.
• Reassign resources for optimal cost-efficiency.
• Reduce non-critical overheads (e.g., travel).
• Re-baseline estimates and reschedule tasks.

## Slide 10: Quality Assurance Strategy
• Phase-based QA gates for design, dev, and UAT.
• Benchmark-based performance metrics.
• Automated testing and peer reviews.
• Sprint-end QA with client stakeholders.

## Slide 11: Improving Communication & Documentation
• Central hub: MS Teams + Planner + SharePoint.
• RACI matrix for role clarity.
• Centralized tracker for progress and issues.
• Controlled document versioning.

## Slide 12: Closing & Q&A
• Strategic and phased project recovery.
• Strong quality and communication frameworks.
• Financial and schedule realignment in progress.
• Ready to lead with accountability and transparency.